## Sheet1
22070-UCC-CE-0908
Attachment 1
Project Description, Line, Substation, or Location | Current Naming Convention for Automation Consistency | Start Construction | Status | Dollars To Date | Expected Completion Date
EASTWOOD_TEXEL | AMPERSEE02_EASTWOOD01 | 2/2027 | Design | 0 | 2027-04-30
MAUMEE_MAPLE STREET | COLLEGEPARK03_MAUMEE01 | 9/2026 | Ready To Construct | 0 | 2026-12-15
COMSTOCK_SHEILDS | COMSTOCK01_RIDGEVIEW02 | 2/2027 | Design | 0 | 2027-04-30
MOSEL_ALLEN | COOLEY02_MOSEL02 | 2/2027 | Design | 0 | 2027-04-30
EAST MUSKEGON_Q.LINE | GETTY01_EAST MUSKEGON03 | 2/2027 | Design | 0 | 2027-04-30
GOGUAC_LAKEVIEW | GOGUAC02_LIBERTY04 | 9/2026 | Ready To Construct | 0 | 2026-12-15
MAPLE GROVE_SUMMIT AVE | MAPLE GRV02_MUSKEGON HGHTS03 | 1/2027 | Obtaining Permits and Easements | 0 | 2027-03-15
MAYNARD_BESTWALL | MAYNARD02_WEALTHY ST02 | 1/2027 | Obtaining Permits and Easements | 0 | 2027-03-15
MONA LAKE_AIRPORT | MONA LAKE01_BROADWAY01 | 1/2027 | Obtaining Permits and Easements | 0 | 2027-03-15
ROBERTS ST_LEROY STREET | OAK ST03_ROBERT ST01 | 9/2026 | Ready To Construct | 0 | 2026-12-15
WEALTHY STREET_NORTHWEST | WEALTHY ST01_DEWEY02 | 2/2027 | Design Complete | 0 | 2027-04-30